## Usage Notes
Ruschlikon Blueprint Two Group
The central market engagement teams have compiled a list of questions aimed at tracking organisations progress towards readiness for phase 1 cutover. The questions cover 8 categories and are accompanied by an expected position at the end of each month leading up to the cutover date. This spreadsheet is intended to provide a mechanism for individual organisations to identify appropriate internal ownership for responding to the questions, and drafting mini plans for each.
The list of questions was originally published in early January, but later revised in early February. A version of this spreadsheet had been shared with members of the Ruschlikon Blueprint Two group prior to the question revisions, and details have been included here on the amendments so that anyone using a previous version can make the appropriate updates. Details provided within each worksheet are identified below, together with an explanation of the intended usage.
There is no guarantee that the list of questions won't be subject to further change. However, I'd anticipate any subsequent changes being primarily against the position expected each month, particularly if the market finds that the cutover date needs to be pushed out a little. It's also possible that new questions could be added as we progress through testing and/or new issues come to light as we get closer to cutover, but deletions are now less likely.
Survey Questions (old)
This worksheet contains the full original list of questions, and the items highlighted in red are the questions that have been removed from the updated list. Anyone using the original spreadsheet can decide what action to take, either continue tracking to them but not reporting on them, or remove the questions altogether.
Survey Questions (new)
This worksheet contains the revised list of questions, with one completely new (row 16) and many questions amended slightly. There have also been quite a lot of updates in relation to the dates included and the expected position each month, all of which have been highlighted. Anyone using the previous version of the spreadsheet may therefore choose to update just these items in their copy rather than starting afresh. Although quite a few of the questions have been re-phrased or had minor additions (e.g. if applicable), there aren't any material differences.
Also includes details of when responses to the questions will be requested, and the progress expected for each month
Questions are broken down into 8 high level topics (column A)
Noting which month the question will be included from (column E)
Outlining the expected progress for each month (columns G to M)
Rating Definitions (copied from original F@L source document)
Gives an indication of the progress expected to achieve the relevant rating level, specified for each of the 8 topics.
Individual Topic Worksheets
The remaining worksheets are for each of the 8 topics. Please note that these were established with an IUA Carrier in mind, there may be other elements that Brokers and/or Managing Agents should consider.
- An owner is specified for each worksheet (cell A1) where we have identified some as individuals, and others as teams. This owner will be responsible for ensuring that progress towards the relevant questions is tracked, and updated at least on a monthly basis.
- A link to the Adoption Guide is provided in row 3, identifying the content that relates to the specific topic for carriers in each worksheet (for ease of reference for worksheet owners).
- Column A is a repeat of the questions, but just for the specific worksheet topic. The colour coding highlights questions that will be included in the February survey.
- Column B contains the survey response values for January (showing the January question colour coding). These are included so that the question owner will be prompted to provide comments on any downgrading due to miscalculation in a prior month, or new information coming to light.
- Column C has the expected progress for February
- Column D is for each question owner (shown in column E) to provide the actual rating for that month
- Column E contains the individual question owner (which may be different to the worksheet owner). These individuals are responsible for providing the actual rating each month, whereas the spreadsheet owner is responsible for ensuring a rating gets applied.
- Column F is to record the individual steps needed to achieve a rating of 4 (complete) or to note specific issues, for example: # January questionnaire included the need to distribute the DPSA to the correct person. We returned a rating of 0 and noted that the DPSA hadn't been issued yet # Activities noted against the question relating to sharing the adoption guide with the relevant parties included i) identify all survey question owners, ii) ensure lead roles are allocated (e.g. test lead, training lead) and iii) provide the pdf and link to all parties identified under i) and ii). At that point we'd be happy to apply a rating of 4 to the question.
- Columns G & H are intended to be used by the question owner to allocate responsibility to specific actions.
- Column I onwards contains week commencing dates for the year, in case anyone wishes to include a high level plan (e.g. dates for training for specific teams). Please don't read too much into it including the whole of 2024, its not a reflection of anticipated progress, just that a similar question set may be useful for preparations towards phase 2.
Monthly updates
At the end of each month, and once we've provided our response for that month, we'll update the colour coding for the following months questions, changing Column B for topic worksheets to reflect the latest responses, and columns C & D ready for the next months data.

## Survey Questions (old)
Value | Scoring | L1 definition
N/A | Not Applicable | Not applicable
0 | Not started | Question asked, zero knowledge/understanding
1 | 25% complete | Just started discussions
2 | 50% complete | Identifying the changes / efforts required
3 | 75% complete | Agreeing detailed requirements and developing the changes
4 | 100% complete | Execution of changes significantly advanced and ready for testing
Survey Questions and related Target & Survey Inclusion Dates | [5 empty] | Position Expected by End of Each Month
Topic | Subtopic | Survey questions | Target date | Included from | If completed, no longer included from | Jan | Feb | Mar | Apr | May | Jun | Jul
1. Project & Change Management | Awareness, commitment and communication | Have you identified all stakeholders that need to be aware of the change including senior leaders, executive team and users of the existing portals and/or support messaging? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Are you holding regular meetings with identified stakeholder groups to drive activity forward? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Have you shared the BP2, phase one adoption guide with all relevant parties within your organisation that will support the change? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | How well does your firm understand the impact of the new deployment plan for BP2, phase 1 on current people, processes and technology (change impact analysis)? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Plan and resourcing | Have you developed an adoption plan (change plan) to manage the changes required under BP2, phase one? This change plan should detail the activities, owners and due dates. | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Plan and resourcing | Have you established project reporting to update stakeholders on the progress of adopting BP2, phase one? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Budgeting | How confident are you that sufficient budget will be made available in 2024 to meet any BP2 development or project costs? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you identified and documented any individuals that currently interact with existing messages? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you documented your current processes that interact with existing messages? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you validated the list of current EDI messages supplied by Velonetic confirming which 'standard' and 'customised' messages you receive today? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Has your IT team and / or service provider compared the structure, format and content of your existing standard messages against the published specifications? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Based on the comparison to published specifications, have you completed an assessment of any changes to the structure, format or content of your existing messages and identified any internal changes needed? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | If applicable, have you taken action to ensure the published variation to any standard EDI messages can be accommodated in time for BP2, phase one adoption? | 2024-03-31 | 2024-01-01 | 2024-04-01 | 2 | 3 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Do you use Writeback messaging? If so, have you checked the technical specifications to ensure alignment with these for continued use? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | If applicable, how far have you progressed in terms of identifying and planning message changes to 'standard' messages? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Have you done the analysis to understand if you currently use customised EDI messaging? | 2023-08-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Have you categorised which custom messages will be taken forward by Velonetic, which will no longer be supported, and which are no longer needed? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Have you decided which, if any, customisations you wish to retain based on those being taken forward? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | For the customised messages that will be supported, have you assessed the cost and obtained internal approval for this? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 1 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | For the customised messages that will not be supported (or that you don't wish to continue with), have you secured the resouces required to revert to the standard EDI version (or determined what workaround process would be needed in the interim)? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Having established any changes to customised messaging, have you documented and signed-off the changes required to the existing messages and added to your change plan? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | If applicable, how far progresssed are you in reverting customised messages back to standard EDI messages? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | Have you established the impact of any message data changes on existing automated process / macro / robotics technology? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | If applicable, have you signed off the approach to make any changes to your current technology based on message data changes? This should be added to your change plan? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | If applicable, how far progressed are you in terms of completing changes to your technology based on your data messaging changes? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | Have you identified how your EDI data is collected from your SFTP site (manually or automated)? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | If applicable, in the case of manual data collection, have you worked with your IT team / service provider to update collection of the data from the new SFPT location? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | If applicable, in the case of automated collection, have you worked with your IT team / service provider to ensure changes are made to support ongoing auto collection from the new SFTP location? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | How far progressed are you in terms of updating the file collection locations? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you obtained your new market gateway security credentials to be able to connect to the market gateway (ASG Adept)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you communicated the changes required to connect to the market gateway (ASG Adpet) to all relevant parties? | 2024-05-31 | 2024-04-01 | 2024-06-01 | 0 | 0 | 0 | 3 | 4 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you shared the credentials with your IT team or service provider, who are responsible for reconfiguring your systems and testing the new gateway? | 2024-04-30 | 2024-04-01 | 2024-05-01 | 0 | 0 | 0 | 4 | 4 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of implementing the new security authentication processes required to connect to the market gateway (ASG Adept)? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of connecting to the market gateway (ASG Adept) to receive messaging from this new origination point? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of updating the collection of data from the new SFTP location? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you assessed which of the portals / applications you use today will be replaced by IPOS, ICOS & Qlik Sense? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you identified and made a list of all users who currently log onto the existing premium, claims and reproting portals / applications? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you reviewed your security specs and worked with your IT team or service provider to ensure users can access the new portals (e.g. is chrome installed/portal urls are white listed etc)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | Have you established if your internal systems interact with any of the portals / applications that will no longer be available? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you documented the impact on any existing technology that will be requried, where your systems interact with the existing portals/applications? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you identified who is going to be responsible for making the changes (e.g. IT team, service provider, etc.), where your systems interact with the existing portals/applications? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you assessed obtained internal approval for the cost of making the changes where your systems interact with the existing portals/applications? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you informed your IT team / service provider of any changes required to internal systems to update the interaction with the new portals/applications? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, having established any changes required to your current technology have you documented and obtained sign-off for the changes required? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Define future state processes | Have you defined and documented your future state business processes for utilising IPOS, ICOS and Qlik Sense (e.g. to manage claims, the claims handler requires login credentials for ICOS) | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Define future state processes | If applicable, have you updated any process documents that you may use? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Vitesse direct settlement services | Have you agreed with the relevant stakeholders in your organisation on whether or not you want to use Vitesse direct settlement? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Vitesse direct settlement services | If applicable, have you decided whether you would like to set up a funded or a non-funded Vitesse account for faster payments? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Vitesse direct settlement services | If applicable, have you advised your customer relationship manager/onboarding lead that you wish to utilise Vitesse direct settlement and indicated the type of account you would like to be set up with (funded/non funded)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you created a list of the reports currently received, and documented how they are collected and who the recipients are? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Based on your report list, have you categorised which existing reports will continue to be used post go-live and highlighted to your engagement partner any reports that are no longer required? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you established and documented which of the reporting and MI portals / applications you use today will be replaced by Qlik Sense? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you identified and made a list of current report owners that will need to access the Qlik Sense tool to download new reports? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you assigned a report owner(s) for each report that will continue to be used? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | Have you established the impact of the current reporting portals being stood down on existing technology / systems, including any impact on any automated processes? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | If applicable, have you documented any actions required to change your technology/systems as a result of the portal changes in your change plan? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | If applicable, have you identified who is going to be responsible for making the changes (IT team and/or a service provider)? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | If applicable, have you assessed the cost and obtained internal approval for the cost of making any changes? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | If applicable, have you informed your IT team/service provider of any changes required to internal systems when the current reporting portals are replaced by self-service reporting on Qlik Sense? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | If applicable, have you documented and obtained sign-off any changes required, and added those changes to your change plan? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you documented your report generation and distribution process today (e.g. Received by email/SFTP and manually actioned or automated processes in place)? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you decided how this process will be updated post phase one go-live when emailing of reports will be replaced by self-service reporting in Qlik Sense or via SFTP? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you documented your future state process and the changes required in users' current ways of working? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
5. Reporting | Impact on business processes | If applicable, where you require reports to be sent to your SFTP site, have you confirmed this with your engagement partner? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
5. Reporting | Impact on business processes | If applicable, have you updated any user manuals to reflect the new reporting process (e.g. report names, collection method etc)? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 2 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you identified a test lead who will be responsible for your testing activity? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 2 | 4 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you indicated your choice of offering (coordinated self-service or enhanced coordinated self-service)? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 2 | 4 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you developed an overall testing plan? | 2024-03-30 | 2024-01-01 | 2024-04-01 | 2 | 3 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you read the test guidance materials from Velonetic? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you identified test scenarios by reviewing the test scenario catalogue or working with a Velonetic test consultant (consultant only available for enhanced coordinated self-serve customers)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you coordinated with your IT/DevOps teams or service provider to set up test data? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Onboarding | Have you nominated a dedicated user administrator who will create new users and secure log in credentials for testing? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Onboarding | Has your administrator set up user accounts and log-ins to onboard all users for testing? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Execution | Have you prepared a test log that tracks which tests scenarios have been run? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Execution | How far have you progressed through the tests in your test plan? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
6. Customer Testing | Execution | Have you been able to get successful results for the tests completed? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training preparation | Have you identified a training lead to manage your training plan? | 2024-01-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you got a training plan in place? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on premiums? Note: the Premiums learning package will contain a module on Qlik Sense reporting | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on claims? Note: the Claims learning packing will contain a module on Qlik Sense reporting | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on LORS? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on user management (user administrators for onboarding)? | 2024-02-29 | 2024-02-01 | 2024-03-01 | 0 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on prop. treaty? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on premiums? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on claims? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on LORS? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on user management (user administrators for onboarding)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on prop treaty? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on premiums? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on claims? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on LORS? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on user management (user administrators for onboarding)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on prop. treaty? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
8. Onboarding | Contractual onboarding | Have you received the Digital Processing Service Agreement (DPSA) for signature? | 2024-01-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Have you passed the DPSA to the correct person to review and sign the agreement? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Has the DPSA been signed? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Has the DPSA been returned to Velonetic? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you nominated a dedicated "user administrator" who will create new users, secure log in credentials and manage new future users / leavers for onboarding prior to go-live? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Has your user administrator received their log-ins and user account? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you identified all users that will need access to the new portals (IPOS, ICOS, and Qlik Sense)? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, and access to IPOS? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, and access to ICOS? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, access to Qlik Sense? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
8. Onboarding | Go-live onboarding | Does your user administrator have access to the knowledge repository with the relevant URLs? | 2024-06-30 | 2024-06-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 0 | 4 | 4
8. Onboarding | Go-live onboarding | Has your user administrator shared URLs your IT team / service provider to ensure they are white labelled to allow access? | 2024-06-30 | 2024-06-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 0 | 4 | 4

## Survey Questions (new)
Value | Scoring | L1 definition
N/A | Not Applicable | Not applicable
0 | Not started | Question asked, zero knowledge/understanding
1 | 25% complete | Just started discussions
2 | 50% complete | Identifying the changes / efforts required
3 | 75% complete | Agreeing detailed requirements and developing the changes
4 | 100% complete | Execution of changes significantly advanced and ready for testing
Survey Questions and related Target & Survey Inclusion Dates | [5 empty] | Position Expected by End of Each Month
Topic | Subtopic | Survey questions | Target date | Included from | If completed, no longer included from | Jan | Feb | Mar | Apr | May | Jun | Jul
1. Project & Change Management | Awareness, commitment and communication | Have you identified all stakeholders that need to be aware of the change including senior leaders, executive team and users of the existing portals and/or support messaging? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Are you holding regular meetings with identified stakeholder groups to drive activity forward? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Have you shared the BP2, phase one adoption guide with all relevant parties within your organisation that will support the change? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Broadly speaking, how well does your firm understand the impact of the new deployment plan for BP2, phase 1 on current people, processes and technology (change impact analysis)? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Awareness, commitment and communication | Has your firm provided final confirmation that it is ready for BP2 Phase 1 go-live? | 2023-06-30 | 2024-05-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 3 | 4 | 4
1. Project & Change Management | Plan and resourcing | Have you developed an adoption plan (change plan) to manage the changes required under BP2, phase one? This change plan should detail the activities, owners and due dates. | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Plan and resourcing | Have you established project reporting to update stakeholders on the progress of adopting BP2, phase one? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1. Project & Change Management | Budgeting | How confident are you that sufficient budget will be made available in 2024 to meet any BP2 development or project costs? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you identified and documented any individuals that currently interact with existing messages? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you documented your current processes that interact with existing messages? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Have you validated the list of current EDI messages supplied by Velonetic confirming which 'standard' and 'customised' messages you receive today? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Has your IT team and / or service provider compared the structure, format and content of your existing standard messages against the published specifications? | 2023-09-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Based on the comparison to published specifications, have you completed an assessment of any changes to the structure, format or content of your existing messages and identified any internal changes needed? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | If applicable, have you taken action to ensure the published variation to any standard EDI messages can be accommodated in time for BP2, phase one adoption? | 2024-03-31 | 2024-01-01 | 2024-04-01 | 2 | 3 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | Do you use Writeback messaging? If so, have you checked the technical specifications to ensure alignment with these for continued use? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on standard messages | If applicable, how far have you progressed in terms of identifying and planning message changes to 'standard' messages? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Have you done the analysis to understand if you currently use customised EDI messaging? | 2023-08-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | Have you categorised which custom messages will be taken forward by Velonetic, which will no longer be supported, and which are no longer needed? | 2023-12-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | If applicable, have you decided which, if any, customisations you wish to retain based on those being supported by Velonetic? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | For the customised messages that will not be supported (or that you don't wish to continue with), have you secured the resources required to revert to the standard/nearest supported customised EDI version (or determined what workaround process would be needed in the interim)? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | If applicable, where you need to move away from unsupported customised messaging, have you documented and signed-off the changes required? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
2. Messaging | Impact on customised messages | If applicable, how far progressed are you in reverting customised messages to the standard/nearest supported customised EDI messages? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | Have you established the potential impact of any message data changes on existing automated process / macro / robotics technology? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | If applicable, have you signed off the approach to make any changes to your current technology based on any message data changes? | 2024-05-31 | 2024-03-01 | 2024-06-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
2. Messaging | Impact on current technology | If applicable, how far progressed are you in terms of completing changes to your technology based on your messaging data changes? | 2024-05-31 | 2024-03-01 | 2024-06-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | Have you identified how your EDI data is collected from your SFTP site (by your service provider or internal manual/automated process)? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
2. Messaging | Impact on file collection | If applicable, in the case of manual EDI data collection, have you worked with your IT team / service provider to update collection of data from the new SFTP location? | 2024-05-31 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
2. Messaging | Impact on file collection | If applicable, in the case of automated EDI data collection, have you worked with your IT team / service provider to ensure changes are made to support ongoing auto collection from the new SFTP location? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
2. Messaging | Impact on file collection | How far progressed are you in terms of updating the file collection locations for EDI data? | 2024-06-30 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you obtained your new market gateway security credentials to be able to connect to the market gateway (ASG Adept)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you communicated the changes required to connect to the market gateway (ASG Adpet) to all relevant parties? | 2024-05-31 | 2024-04-01 | 2024-06-01 | 0 | 0 | 0 | 3 | 4 | 4 | 4
3. Market Gateway | New end points address and credentials | Have you shared the new market gateway (ASG Adept) security credentials with your IT team or service provider, who are responsible for reconfiguring your systems and testing the new gateway? | 2024-04-30 | 2024-04-01 | 2024-05-01 | 0 | 0 | 0 | 4 | 4 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of implementing the new security authentication processes required to connect to the market gateway (ASG Adept)? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of connecting to the market gateway (ASG Adept) to receive messaging from this new origination point? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
3. Market Gateway | New security authentication process | How far has your IT team or service provider progressed in terms of updating the collection of data from the new SFTP location? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you assessed which of the portals / applications you use today will be replaced by IPOS and ICOS? | 2023-11-30 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you identified and made a list of all users who currently log onto the existing premium, claims and reporting portals / applications? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current portals and users | Have you reviewed your security specs and worked with your IT team or service provider to ensure users can access the new portals (e.g. is chrome installed/portal urls are white listed etc)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | Have you established if your internal systems interact with any of the portals / applications that will no longer be available? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you documented the impact on any existing technology that will be required, where your systems interact with the existing portals/applications? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 1 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you identified who is going to be responsible for making the changes (e.g. IT team, service provider, etc.), where your systems interact with the existing portals/applications? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 1 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Impact on current technology | If applicable, have you assessed and obtained internal approval for the cost of making the changes where your systems interact with the existing portals/applications? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 1 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Define future state processes | Have you defined your future state business processes for utilising IPOS, ICOS and Qlik Sense (e.g. to manage claims, the claims handler requires login credentials for ICOS and to progress a claim through ICOS) | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
4. Digital Services | Define future state processes | If applicable, have you updated any process documents that you may use in relation to existing portals/applications? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
4. Digital Services | Vitesse direct settlement services | Have you agreed with the relevant stakeholders in your organisation on whether or not you want to use Vitesse direct settlement? | 2024-05-31 | 2024-03-01 | 2024-07-01 | 0 | 0 | 1 | 2 | 3 | 4 | 4
4. Digital Services | Vitesse direct settlement services | If applicable, have you decided whether you would like to set up a funded or a non-funded Vitesse account for faster payments? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
4. Digital Services | Vitesse direct settlement services | If applicable, have you advised your customer relationship manager/onboarding lead that you wish to utilise Vitesse direct settlement and indicated the type of account you would like to be set up with (funded/non funded)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you created a list of the reports currently received, and documented how they are collected and who the recipients are? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Based on your report list, have you categorised which existing reports will continue to be used post go-live and highlighted to your engagement partner any reports that are no longer required? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you established and documented which of the reporting and MI portals / applications you use today will be replaced by Qlik Sense? | 2024-04-30 | 2024-01-01 | 2024-05-01 | 1 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you identified and made a list of current report owners that will need to access the Qlik Sense tool to download new reports? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current reports and users | Have you assigned a report owner(s) for each report that will continue to be used? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on current technology | Have you established the impact of the current reporting portals being stood down on existing technology / systems, including any impact on any automated processes? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you documented your report generation and distribution process today (e.g. Received by email/SFTP and manually actioned or automated processes in place)? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you decided how this report generation and distribution process will be updated for phase one go-live when emailing of reports will be replaced by self-service reporting in Qlik Sense or via SFTP? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
5. Reporting | Impact on business processes | Have you documented your future state reporting process and the changes required in users' current ways of working? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
5. Reporting | Impact on business processes | If applicable, where you require report data to be sent to your SFTP site, have you confirmed this with your engagement partner? | 2024-05-31 | 2024-02-01 | 2024-06-01 | 0 | 1 | 2 | 3 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you identified a test lead who will be responsible for your testing activity? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 2 | 4 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you indicated your choice of test offering (coordinated self-service or enhanced coordinated self-service)? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 2 | 4 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you developed an overall testing plan? | 2024-03-30 | 2024-01-01 | 2024-04-01 | 2 | 3 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you read the test guidance materials from Velonetic? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you identified test scenarios by reviewing the test scenario catalogue or working with a Velonetic test consultant (consultant only available for enhanced coordinated self-serve customers)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Preparation | Have you coordinated with your IT/DevOps teams or service provider to set up test data? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Onboarding | Have you nominated a dedicated user administrator who will create new users and secure log in credentials for testing? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
6. Customer Testing | Onboarding | Has your administrator set up user accounts and log-ins to onboard all users for testing? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
6. Customer Testing | Execution | Have you prepared a test log that tracks which tests scenarios have been run? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
6. Customer Testing | Execution | How far have you progressed through the tests in your test plan? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
6. Customer Testing | Execution | Have you been able to get successful results for the tests completed? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training preparation | Have you identified a training lead to manage your training plan? | 2024-01-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you got a training plan in place? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on premiums? Note: the Premiums learning package will contain a module on Qlik Sense reporting | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on claims? Note: the Claims learning package will contain a module on Qlik Sense reporting | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | If applicable, have you identified all users that will require training on LORS? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 3 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you identified all users that will require training on user management (user administrators for onboarding)? | 2024-02-29 | 2024-02-01 | 2024-03-01 | 0 | 4 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | If applicable, have you identified all users that will require training on prop. treaty? | 2024-04-30 | 2024-02-01 | 2024-05-01 | 0 | 2 | 3 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on premiums? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on claims? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on LORS? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on user management (user administrators for onboarding)? | 2024-03-31 | 2024-03-01 | 2024-04-01 | 0 | 0 | 4 | 4 | 4 | 4 | 4
7. Training | Training preparation | Have you scheduled in all people that require training on prop treaty? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on premiums? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on claims? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on LORS? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on user management (user administrators for onboarding)? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 3 | 4 | 4 | 4 | 4
7. Training | Training delivery and completion | Have all users been trained on prop. treaty? | 2024-06-30 | 2024-04-01 | 2024-07-01 | 0 | 0 | 0 | 2 | 3 | 4 | 4
8. Onboarding | Contractual onboarding | Have you received the Digital Processing Service Agreement (DPSA) documents for signature? | 2024-01-31 | 2024-01-01 | 2024-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Have you passed the DPSA documents to the correct person(s) to review and sign? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Have the DPSA documents been signed? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
8. Onboarding | Contractual onboarding | Have the signed DPSA documents been returned to Velonetic? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you nominated a dedicated "user administrator" who will create new users, secure log in credentials and manage new future users / leavers for onboarding prior to go-live? | 2024-02-29 | 2024-01-01 | 2024-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Has your user administrator received their log-ins and user account? | 2024-04-30 | 2024-03-01 | 2024-05-01 | 0 | 0 | 2 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you identified all users that will need access to the new portals (IPOS, ICOS, and Qlik Sense)? | 2024-03-31 | 2024-02-01 | 2024-04-01 | 0 | 2 | 4 | 4 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, and access to IPOS? | 2024-05-31 | 2024-05-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, and access to ICOS? | 2024-05-31 | 2024-05-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Have you set up all identified users with user accounts, access to Qlik Sense? | 2024-05-31 | 2024-05-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Does your user administrator have access to the knowledge repository with the relevant URLs? | 2024-05-31 | 2024-05-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 4 | 4 | 4
8. Onboarding | Go-live onboarding | Has your user administrator shared URLs your IT team / service provider to ensure they are white labelled to allow access? | 2024-05-31 | 2024-05-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 4 | 4 | 4

## Rating Definitions
Value | Scoring | L1 definition | 1. Project and Change Management | 2. Messaging | 3. Market gateway (ASG Adept) | 4. Digital services | 5. Reporting | 6. Customer testing | 7. Training | 8. Onboarding
N/A | Not Applicable | Not applicable | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value | Question not relevant/ nil value
0 | Not started | Question asked, zero knowledge/understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding | Question asked, zero knowledge or understanding
1 | 25% complete | Just started discussions | The firm has made little to no progress in addressing the specific aspect of change adoption. There is no evidence of identification, or planning, and there is a high level of uncertainty or inadequacy in the associated area. | The firm has taken minimal or no steps towards addressing the changes to standard / customised messaging. There is no clear identification of the changes / no comparison to published specs / no documenting changes in the change plan / no strategy or budget in place. The execution of changes to messaging and file collection locations has not begun. | The firm has made minimal or no progress in preparing to connect to the new market gateway. Security credentials have not been obtained, and there is no communication or planning regarding necessary technical changes. Implementation of new security authentication processes and data collection from the new SFTP location has not started. | The firm has made minimal or no progress in preparing for the transition to new digital processing services. There is no clear identification of existing portals to be replaced or of impacted users. Future processes are undefined, and there's no documentation or assessment of the impact on existing technology or required changes. | The firm has made minimal or no progress in preparing for the transition to Qlik sense. There is no clear identification of portals / apps to be replaced or of impacted users. Future processes are undefined, and there is no assessment of the impact on existing technology or documented changes. Conversations on resourcing, budgeting, testing and training needs have not started. | The firm has shown no progress or very limited effort in the specified aspect of testing. There is no identified test lead, overall testing plan, or prepared test scenarios. Lack of a dedicated user administrator, user accounts, and log-ins for testing. Absence of a test log, progress through the test plan, and successful results for completed tests. | The firm has shown no progress in the specified aspect of training. Users requiring training have not been identified, or scheduled in for training. | The firm has shown no progress in the specified aspect of onboarding. Users requiring onboarding / new profiles have not been identified, the DPSA has not be reviewed / signed and onboarding data not sent. The user administrator does not yet have access to the Knowledge Repository, hence no URL distribution or user set-up.
2 | 50% complete | Identifying the changes / efforts required | The firm has taken some initial steps, but has not fully addressed the specific aspect of adoption There is partial identification or planning, and there are noticeable gaps or uncertainties in the related area (e.g. basic communication, rudimentary plan, insufficient resources/budget, little project management in place). | The firm has taken some initial steps, but has not fully addressed the has initiated some preliminary steps but has not fully addressed the changes to messaging standards. There is partial identification of changes, and some initial planning. A strategy / estimation of costs for reverting to EDI messaging is in development, but is not finalized. Progress toward executing changes and updating file collection locations is minimal. | The firm has initiated some preliminary steps but has not fully addressed the transition to the new market gateway (ASG Adept). Obtaining security credentials may be in progress, and there's some communication about technical changes. However, these changes are not fully established, and progress in implementing new security authentication processes and data collection is limited. | The firm has initiated some preliminary steps but has not fully addressed the transition to new digital processing services. There is partial identification of portals to be replaced, some understanding of impacted users, and limited progress on obtaining login credentials. Future processes are under development, but there's limited documentation and assessment of the impact on existing technology. | The firm has initiated some preliminary steps but has not fully addressed the transition to the new self-serve reporting tool. There is partial documentation of the portals to be replaced, some understanding of impacted users, and a basic assessment of the impact on existing technology (and some documentation of required changes). Resourcing and budget are in progress, but there is limited communication with the IT team or service provider. | The firm has made limited progress in identifying a test lead, developing an overall testing plan, and preparing test scenarios. Initial steps taken to identify a dedicated user administrator and set up user accounts. Limited progress in test log preparation, advancing through the test plan, and obtaining successful results for completed tests. | The firm has shown limited progress with basic efforts relating to training. Some users have been identified for training, and scheduling of training sessions has started. | The firm has shown limited progress with basic efforts relating to onboarding. Some users have been identified for onboarding, the DPSA received and preliminary steps taken for login credentials and user set-up.
3 | 75% complete | Agreeing detailed requirements and developing the changes | The firm has a reasonable level of awareness and commitment to the proposed change, and has made substantial progress in addressing the specific aspect of adoption. Communication is fairly effective, and a solid plan is in place, though some key resources may be lacking. Budgeting is underway, and there is a basic project management framework in place. There may be some areas that still require attention or improvement. | The firm has made substantial progress in addressing the changes to messaging standards. There is a clear identification of changes, a comprehensive gap analysis evident within the change plan. A well-defined strategy and budget are in place for moving away from customised messaging (if applicable), though there may be some finalisation and refinement required. Execution of changes has commenced, and work on updating file collection locations is underway. There may be some areas that still require attention or improvement. | The firm has made substantial progress in getting ready to connect to the new market gateway (ASG Adept). Security credentials are obtained or in the final stages, and technical changes have been communicated to relevant parties. Implementation of new security authentication processes is underway, and work on updating data collection from the new SFTP locations is near completion. There may be some areas that still require attention or improvement. | The firm has made substantial progress in preparing for the transition to new digital processing services. Existing portals to be replaced are identified in the majority, impacted users are known. Future processes are more or less defined, and there is documentation and a reasonable assessment of the impact on existing technology and required changes (with IT team / service provider now in the loop). There may be some areas that still require attention or improvement. | The firm has made substantial progress in preparing for the transition to the new self-serve reporting tool. Existing reporting portals to be replaced are mostly documented, impacted users are known, and a reasonable assessment of the impact on existing technology has taken place. Resourcing and budget is agreed, and there is communication with the IT team or service provider. Future processes are more or less defined, and there is documentation of required changes. Login credentials are in the process of being obtained, and there is ongoing testing and identification of training needs. There may be some areas that still require attention or improvement. | The firm has made substantial progress in identifying a test lead, finalising a testing plan, and preparing comprehensive test scenarios. Active involvement of a dedicated user administrator and successfully set up user accounts / log-ins. A test log is prepared, and the firm is making its way through the test plan. Successful results received on a number of completed tests. | The firm has made substantial progress in the various aspects of training. Almost all users in need of training have been identified, scheduled for training, and training delivery is in progress. | The firm has made substantial progress in the various aspects of onboarding. Almost all users have been identified for onboarding, the DPSA received and reviewed, and securing of login credentials / user set-up is underway.
4 | 100% complete | Execution of changes significantly advanced and ready for testing | The firm appears to be well-prepared and highly committed to the proposed change. Communication is comprehensive and effective, and a well-defined plan is in place with adequate resources. Budgeting is sufficient (and validated), and there is a robust project management system for effective implementation. | The firm appears to be well-prepared and highly committed to implementing changes to messaging. Changes are thoroughly identified, a comprehensive gap analysis has been conducted, and detailed plans are in place. The strategy is well-defined for moving away from customised messaging, and the budget has been signed off (if applicable). Execution of changes is significantly advanced, and file collection locations have been updated as needed. | The firm appears to be well-prepared and highly committed to connecting to the new market gateway (ASG Adept). Security credentials are in place, and all necessary technical changes have been established and communicated effectively. New security authentication processes have been implemented, and data collection from the new SFTP location is complete. | The firm appears to be well-prepared and highly committed to transitioning to new digital processing services and replacing existing portals. Existing portals have been identified, impacted users are understood and have been notified of the changes. Login credentials have also been secured and tested. Future processes are well-defined and validated, and there is comprehensive documentation and a thorough assessment of the impact on existing technology and required changes (with all relevant stakeholders aware of their role to play in implementing the changes and execution of changes significantly advanced). | Confidently ready: The firm appears to be well-prepared and highly committed to transitioning to the new self-serve reporting tool. Existing portals have been thoroughly documented, impacted users are well known and have been notified of the changes, and the impact on existing technology is well assessed. Resourcing and budget are secured and validated, and there is effective communication with the IT team or service provider. Future processes are well-defined and validated, and there is comprehensive documentation and a thorough assessment of the impact on existing technology and required changes (with all relevant stakeholders aware of their role to play in implementing the changes and execution of changes significantly advanced). | Confidently ready: The firm appears to be well-prepared and highly committed to testing with a proficient test lead. A well-structured testing plan is finalised with thorough identification of scenarios. Active participation of a dedicated user administrator, successfully set up user accounts / log-ins, and a comprehensive test log. Substantial progress has been made in executing the test plan, with high success rates for completed tests. | The firm appears to be well-prepared and highly committed to training. All users requiring training are identified, scheduled in for training and training has been successfully delivered. | The firm appears to be well-prepared and highly committed to onboarding. All users requiring onboarding are identified, DPSA is signed and returned to Velonetic, log in credentials secured and new users set-up and access tested by the user administrator.
Score | Selection |  | Definition(s)
Scoring |  |  | Comprehension style questions | Readiness Style questions | Training Style questions
N/A | Not Applicable
0 | Not started |  | Question not asked/nil value | Question not asked/nil value | Received nothing
1 | 25% complete |  | Question asked, zero knowledge/understanding | Question asked, zero knowledge/understanding | Seen Material
2 | 50% complete |  | Basic level knowledge/understanding | Just started discussions | Received Traning Material
3 | 75% complete |  | Low level knowledge/understanding | Agreeing detailed requirements | Received Train the Trainer material
4 | 100% complete |  | Medium level knowledge/understanding | Developing the changes | Trained the teams
|  |  | High level knowledge/understanding | Testing the changes | Onboarded
|  |  | Expert level knowledge/understanding | Ready to release changes | Ready for go live

## 1 - Project & Change Mgmt
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | Contains Carrier Adoption Activities in slides 38 to 49, and Carrier pathway in 32 to 37 | [6 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you identified all stakeholders that need to be aware of the change including senior leaders, executive team and users of the existing portals and/or support messaging? |  | 4
Are you holding regular meetings with identified stakeholder groups to drive activity forward? |  | 4
Have you shared the BP2, phase one adoption guide with all relevant parties within your organisation that will support the change? |  | 4
Broadly speaking, how well does your firm understand the impact of the new deployment plan for BP2, phase 1 on current people, processes and technology (change impact analysis)? |  | 4
Has your firm provided final confirmation that it is ready for BP2 Phase 1 go-live?
Have you developed an adoption plan (change plan) to manage the changes required under BP2, phase one? This change plan should detail the activities, owners and due dates. |  | 4
Have you established project reporting to update stakeholders on the progress of adopting BP2, phase one? |  | 4
How confident are you that sufficient budget will be made available in 2024 to meet any BP2 development or project costs? |  | 4

## 2 - Messaging
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | Carrier Messaging Specifications in slides 50 to 53 | [6 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you identified and documented any individuals that currently interact with existing messages? |  | 4
Have you documented your current processes that interact with existing messages? |  | 4
Have you validated the list of current EDI messages supplied by Velonetic confirming which 'standard' and 'customised' messages you receive today? |  | 4
Has your IT team and / or service provider compared the structure, format and content of your existing standard messages against the published specifications? |  | 4
Based on the comparison to published specifications, have you completed an assessment of any changes to the structure, format or content of your existing messages and identified any internal changes needed? |  | 4
If applicable, have you taken action to ensure the published variation to any standard EDI messages can be accommodated in time for BP2, phase one adoption? |  | 3
Do you use Writeback messaging? If so, have you checked the technical specifications to ensure alignment with these for continued use? |  | 4
If applicable, how far have you progressed in terms of identifying and planning message changes to 'standard' messages? |  | 2
Have you done the analysis to understand if you currently use customised EDI messaging? |  | 4
Have you categorised which custom messages will be taken forward by Velonetic, which will no longer be supported, and which are no longer needed? |  | 4
If applicable, have you decided which, if any, customisations you wish to retain based on those being supported by Velonetic? |  | 2
For the customised messages that will not be supported (or that you don't wish to continue with), have you secured the resources required to revert to the standard/nearest supported customised EDI version (or determined what workaround process would be needed in the interim)? |  | 2
If applicable, where you need to move away from unsupported customised messaging, have you documented and signed-off the changes required?
If applicable, how far progressed are you in reverting customised messages to the standard/nearest supported customised EDI messages?
Have you established the potential impact of any message data changes on existing automated process / macro / robotics technology? |  | 2
If applicable, have you signed off the approach to make any changes to your current technology based on any message data changes?
If applicable, how far progressed are you in terms of completing changes to your technology based on your messaging data changes?
Have you identified how your EDI data is collected from your SFTP site (by your service provider or internal manual/automated process)? |  | 2
If applicable, in the case of manual EDI data collection, have you worked with your IT team / service provider to update collection of data from the new SFTP location?
If applicable, in the case of automated EDI data collection, have you worked with your IT team / service provider to ensure changes are made to support ongoing auto collection from the new SFTP location?
How far progressed are you in terms of updating the file collection locations for EDI data?

## 3 - Market Gateway
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | [7 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you obtained your new market gateway security credentials to be able to connect to the market gateway (ASG Adept)?
Have you communicated the changes required to connect to the market gateway (ASG Adpet) to all relevant parties?
Have you shared the new market gateway (ASG Adept) security credentials with your IT team or service provider, who are responsible for reconfiguring your systems and testing the new gateway?
How far has your IT team or service provider progressed in terms of implementing the new security authentication processes required to connect to the market gateway (ASG Adept)?
How far has your IT team or service provider progressed in terms of connecting to the market gateway (ASG Adept) to receive messaging from this new origination point?
How far has your IT team or service provider progressed in terms of updating the collection of data from the new SFTP location?

## 4 - Digital Services
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | Portals & applications slides 54 to 58 | [6 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you assessed which of the portals / applications you use today will be replaced by IPOS and ICOS? |  | 4
Have you identified and made a list of all users who currently log onto the existing premium, claims and reporting portals / applications? |  | 4
Have you reviewed your security specs and worked with your IT team or service provider to ensure users can access the new portals (e.g. is chrome installed/portal urls are white listed etc)?
Have you established if your internal systems interact with any of the portals / applications that will no longer be available? |  | 2
If applicable, have you documented the impact on any existing technology that will be required, where your systems interact with the existing portals/applications? |  | 1
If applicable, have you identified who is going to be responsible for making the changes (e.g. IT team, service provider, etc.), where your systems interact with the existing portals/applications? |  | 1
If applicable, have you assessed and obtained internal approval for the cost of making the changes where your systems interact with the existing portals/applications? |  | 1
Have you defined your future state business processes for utilising IPOS, ICOS and Qlik Sense (e.g. to manage claims, the claims handler requires login credentials for ICOS and to progress a claim through ICOS) |  | 1
If applicable, have you updated any process documents that you may use in relation to existing portals/applications? |  | 1
Have you agreed with the relevant stakeholders in your organisation on whether or not you want to use Vitesse direct settlement?
If applicable, have you decided whether you would like to set up a funded or a non-funded Vitesse account for faster payments?
If applicable, have you advised your customer relationship manager/onboarding lead that you wish to utilise Vitesse direct settlement and indicated the type of account you would like to be set up with (funded/non funded)?

## 5 - Reporting
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | Reports on slides 46 & 47 | [6 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you created a list of the reports currently received, and documented how they are collected and who the recipients are? |  | 2
Based on your report list, have you categorised which existing reports will continue to be used post go-live and highlighted to your engagement partner any reports that are no longer required? |  | 2
Have you established and documented which of the reporting and MI portals / applications you use today will be replaced by Qlik Sense? |  | 2
Have you identified and made a list of current report owners that will need to access the Qlik Sense tool to download new reports? |  | 2
Have you assigned a report owner(s) for each report that will continue to be used? |  | 2
Have you established the impact of the current reporting portals being stood down on existing technology / systems, including any impact on any automated processes? |  | 2
Have you documented your report generation and distribution process today (e.g. Received by email/SFTP and manually actioned or automated processes in place)? |  | 2
Have you decided how this report generation and distribution process will be updated for phase one go-live when emailing of reports will be replaced by self-service reporting in Qlik Sense or via SFTP? |  | 2
Have you documented your future state reporting process and the changes required in users' current ways of working? |  | 1
If applicable, where you require report data to be sent to your SFTP site, have you confirmed this with your engagement partner? |  | 1

## 6 - Customer Testing
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | Market testing on slides 48 & 49 | [6 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you identified a test lead who will be responsible for your testing activity? |  | 4
Have you indicated your choice of test offering (coordinated self-service or enhanced coordinated self-service)? |  | 4
Have you developed an overall testing plan? |  | 3
Have you read the test guidance materials from Velonetic?
Have you identified test scenarios by reviewing the test scenario catalogue or working with a Velonetic test consultant (consultant only available for enhanced coordinated self-serve customers)?
Have you coordinated with your IT/DevOps teams or service provider to set up test data?
Have you nominated a dedicated user administrator who will create new users and secure log in credentials for testing? |  | 3
Has your administrator set up user accounts and log-ins to onboard all users for testing?
Have you prepared a test log that tracks which tests scenarios have been run?
How far have you progressed through the tests in your test plan?
Have you been able to get successful results for the tests completed?

## 7 - Training
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Training material ¦ Velonetic | [7 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you identified a training lead to manage your training plan? |  | 4
Have you got a training plan in place? |  | 4
Have you identified all users that will require training on premiums? Note: the Premiums learning package will contain a module on Qlik Sense reporting |  | 3
Have you identified all users that will require training on claims? Note: the Claims learning package will contain a module on Qlik Sense reporting |  | 3
If applicable, have you identified all users that will require training on LORS? |  | 3
Have you identified all users that will require training on user management (user administrators for onboarding)? |  | 4
If applicable, have you identified all users that will require training on prop. treaty? |  | 2
Have you scheduled in all people that require training on premiums?
Have you scheduled in all people that require training on claims?
Have you scheduled in all people that require training on LORS?
Have you scheduled in all people that require training on user management (user administrators for onboarding)?
Have you scheduled in all people that require training on prop treaty?
Have all users been trained on premiums?
Have all users been trained on claims?
Have all users been trained on LORS?
Have all users been trained on user management (user administrators for onboarding)?
Have all users been trained on prop. treaty?

## 8 - Onboarding
Worksheet Owner:
February questions highlighted | [7 empty] | 2024
Adoption guide ¦ Blueprint Two (velonetic.co.uk) | [7 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Survey Question | Jan Reported | Feb Target | Current Rating | Owner | Activity or Issue | Owner | Involved | 1st Jan | 8th Jan | 15th Jan | 22nd Jan | 29th Jan | 5th Feb | 12th Feb | 19th Feb | 26th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 3rd Jun | 10th Jun | 17th Jun | 24th Jun | 1st Jul | 8th Jul | 15th Jul | 22nd Jul | 29th Jul | 5th Aug | 12th Aug | 19th Aug | 26th Aug | 2nd Sep | 9th Sep | 16th Sep | 23rd Sep | 30th Sep | 7th Oct | 14th Oct | 21st Oct | 28th Oct | 4th Nov | 11th Nov | 18th Nov | 25th Nov | 2nd Dec | 9th Dec | 16th Dec | 23rd Dec | 30th Dec
Have you received the Digital Processing Service Agreement (DPSA) documents for signature? |  | 4
Have you passed the DPSA documents to the correct person(s) to review and sign? |  | 4
Have the DPSA documents been signed?
Have the signed DPSA documents been returned to Velonetic?
Have you nominated a dedicated "user administrator" who will create new users, secure log in credentials and manage new future users / leavers for onboarding prior to go-live? |  | 4
Has your user administrator received their log-ins and user account?
Have you identified all users that will need access to the new portals (IPOS, ICOS, and Qlik Sense)? |  | 2
Have you set up all identified users with user accounts, and access to IPOS?
Have you set up all identified users with user accounts, and access to ICOS?
Have you set up all identified users with user accounts, access to Qlik Sense?
Does your user administrator have access to the knowledge repository with the relevant URLs?
Has your user administrator shared URLs your IT team / service provider to ensure they are white labelled to allow access?